## data
Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Total | Work to be done for a day | Work done for a day
Gemini | Task 1 | Hirsch | 4387800% | 5 | 4388200% | 2 | 40% | 100 | 20 | 20%
Gemini | Task 2 | Samora | 4387800% | 6 | 4388500% | 3 | 50% | 100 | 16.6667 | 16.67%
Gemini | Task 3 | McFay | 4387900% | 10 | 4389200% | 4 | 40% | 100 | 10 | 10%
Gemini | Task 4 | Wood | 4388200% | 9 | 4389400% | 3 | 33.33% | 100 | 11.1111 | 11.11%
Gemini | Task 5 | Ladd | 4387800% | 4 | 4388100% | 1 | 25% | 100 | 25 | 25%
Gemini | Task 6 | Hirsch | 4388100% | 6 | 4388800% | 0 | 0% | 100 | 16.6667 | #DIV/0!
Gemini | Task 7 | Samora | 4388100% | 7 | 4388900% | 3 | 42.86% | 100 | 14.2857 | 14.29%
Gemini | Task 8 | McFay | 4388500% | 5 | 4388900% | 2 | 40% | 100 | 20 | 20%
Gemini | Task 9 | Wood | 4388500% | 9 | 4389500% | 1 | 11.11% | 100 | 11.1111 | 11.11%
Gemini | Task 10 | Ladd | 4388500% | 6 | 4389200% | 3 | 50% | 100 | 16.6667 | 16.67%
Orion | Task 1 | Hirsch | 4387900% | 7 | 4388700% | 7 | 100% | 100 | 14.2857 | 14.29%
Orion | Task 2 | Samora | 4387800% | 9 | 4388800% | 4 | 44.44% | 100 | 11.1111 | 11.11%
Orion | Task 3 | McFay | 4387900% | 8 | 4388800% | 0 | 0% | 100 | 12.5 | #DIV/0!
Orion | Task 4 | Wood | 4388100% | 7 | 4388900% | 3 | 42.86% | 100 | 14.2857 | 14.29%
Orion | Task 5 | Ladd | 4388200% | 4 | 4388700% | 1 | 25% | 100 | 25 | 25%
Orion | Task 6 | Hirsch | 4388200% | 6 | 4388900% | 3 | 50% | 100 | 16.6667 | 16.67%
Orion | Task 7 | Samora | 4388500% | 6 | 4389200% | 5 | 83.33% | 100 | 16.6667 | 16.67%
Orion | Task 8 | McFay | 4388600% | 4 | 4388900% | 1 | 25% | 100 | 25 | 25%
Orion | Task 9 | Wood | 4388800% | 7 | 4389600% | 3 | 42.86% | 100 | 14.2857 | 14.29%
Orion | Task 10 | Ladd | 4387800% | 3 | 4388000% | 3 | 100% | 100 | 33.3333 | 33.33%
Vega | Task 1 | Hirsch | 4387800% | 10 | 4388900% | 5 | 50% | 100 | 10 | 10%
Vega | Task 2 | Samora | 4388200% | 5 | 4388800% | 4 | 80% | 100 | 20 | 20%
Vega | Task 3 | McFay | 4388500% | 7 | 4389300% | 3 | 42.86% | 100 | 14.2857 | 14.29%
Vega | Task 4 | Wood | 4388700% | 7 | 4389500% | 2 | 28.57% | 100 | 14.2857 | 14.29%
Vega | Task 5 | Ladd | 4388900% | 3 | 4389300% | 2 | 66.67% | 100 | 33.3333 | 33.33%
Delta | Task 1 | Hirsch | 4389200% | 9 | 4390200% | 8 | 88.89% | 100 | 11.1111 | 11.11%
Delta | Task 2 | Samora | 4389200% | 10 | 4390300% | 2 | 20% | 100 | 10 | 10%
Delta | Task 3 | McFay | 4387800% | 4 | 4388100% | 0 | 0% | 100 | 25 | #DIV/0!
Delta | Task 4 | Wood | 4388000% | 8 | 4388900% | 5 | 62.5% | 100 | 12.5 | 12.5%
Delta | Task 5 | Ladd | 4388500% | 10 | 4389600% | 3 | 30% | 100 | 10 | 10%
Delta | Task 6 | Hirsch | 4388600% | 6 | 4389300% | 3 | 50% | 100 | 16.6667 | 16.67%
Delta | Task 7 | Samora | 4388600% | 4 | 4388900% | 2 | 50% | 100 | 25 | 25%
Alpha | Task 1 | McFay | 4388900% | 8 | 4390000% | 3 | 37.5% | 100 | 12.5 | 12.5%
Alpha | Task 2 | Wood | 4389200% | 9 | 4390200% | 4 | 44.44% | 100 | 11.1111 | 11.11%
Alpha | Task 3 | Ladd | 4388100% | 5 | 4388700% | 3 | 60% | 100 | 20 | 20%
Alpha | Task 4 | Hirsch | 4388000% | 3 | 4388200% | 3 | 100% | 100 | 33.3333 | 33.33%
Alpha | Task 5 | Samora | 4388200% | 7 | 4389200% | 3 | 42.86% | 100 | 14.2857 | 14.29%
Alpha | Task 6 | McFay | 4388500% | 10 | 4389600% | 2 | 20% | 100 | 10 | 10%
Alpha | Task 7 | Wood | 4388500% | 10 | 4389600% | 3 | 30% | 100 | 10 | 10%
Alpha | Task 8 | Ladd | 4388500% | 3 | 4388700% | 0 | 0% | 100 | 33.3333 | #DIV/0!
Formulas:
End Date = WORKDAY.INTL(Table13[[#This Row],[Start Date]]-1,Table13[[#This Row],[Duration]],1)
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## progress
Project | (All) |  | Progress for each projext and overall based on tasks
Row Labels | Average of Progress |  | Obj: Analysing avg progress for each tasks under each project which will give us an idea of status.
Task 1 | 0.63278
Task 10 | 0.75
Task 2 | 0.47778
Task 3 | 0.28571
Task 4 | 0.53452
Task 5 | 0.37905
Task 6 | 0.3
Task 7 | 0.51548
Task 8 | 0.21667
Task 9 | 0.26984
Grand Total | 0.43752
Project | Alpha | Project | Delta | Project | Gemini
Row Labels | Average of Progress | Row Labels | Average of Progress | Row Labels | Average of Progress
Task 1 | 0.375 | Task 1 | 0.88889 | Task 1 | 0.4
Task 2 | 0.44444 | Task 2 | 0.2 | Task 10 | 0.5
Task 3 | 0.6 | Task 3 | 0 | Task 2 | 0.5
Task 4 | 1 | Task 4 | 0.625 | Task 3 | 0.4
Task 5 | 0.42857 | Task 5 | 0.3 | Task 4 | 0.33333
Task 6 | 0.2 | Task 6 | 0.5 | Task 5 | 0.25
Task 7 | 0.3 | Task 7 | 0.5 | Task 6 | 0
Task 8 | 0 | Grand Total | 0.43056 | Task 7 | 0.42857
Grand Total | 0.4185 |  |  | Task 8 | 0.4
|  |  |  | Task 9 | 0.11111
|  |  |  | Grand Total | 0.3323
Project | Orion | Project | Vega
Row Labels | Average of Progress | Row Labels | Average of Progress
Task 1 | 1 | Task 1 | 0.5
Task 10 | 1 | Task 2 | 0.8
Task 2 | 0.44444 | Task 3 | 0.42857
Task 3 | 0 | Task 4 | 0.28571
Task 4 | 0.42857 | Task 5 | 0.66667
Task 5 | 0.25 | Grand Total | 0.53619
Task 6 | 0.5
Task 7 | 0.83333
Task 8 | 0.25
Task 9 | 0.42857
Grand Total | 0.51349

## workhours
WORKHOURS FOR EACH PROJECT |  |  | Example- for Alpha |  |  |  | Obj: To analyse the total workhours under each project and the most time consuming proj
Project | Alpha
Sum of Duration | Column Labels
Row Labels | Hirsch | Ladd | McFay | Samora | Wood | Grand Total
Task 1 |  |  | 8 |  |  | 8
Task 2 |  |  |  |  | 9 | 9
Task 3 |  | 5 |  |  |  | 5
Task 4 | 3 |  |  |  |  | 3
Task 5 |  |  |  | 7 |  | 7
Task 6 |  |  | 10 |  |  | 10
Task 7 |  |  |  |  | 10 | 10
Task 8 |  | 3 |  |  |  | 3
Grand Total | 3 | 8 | 18 | 7 | 19 | 55

## Efficiency
Project | Alpha | [5 empty] | Project | Delta
Sum of Progress | Days completed | [5 empty] | Sum of Progress | Days completed
Tasks | 0 | 2 | 3 | 4 | Grand Total |  | Tasks | 0 | 2 | 3 | 5 | 8 | Grand Total
Task 1 |  |  | 0.375 |  | 0.375 |  | Task 1 |  |  |  |  | 0.88889 | 0.88889
Task 2 |  |  |  | 0.44444 | 0.44444 |  | Task 2 |  | 0.2 |  |  |  | 0.2
Task 3 |  |  | 0.6 |  | 0.6 |  | Task 3 | 0 |  |  |  |  | 0
Task 4 |  |  | 1 |  | 1 |  | Task 4 |  |  |  | 0.625 |  | 0.625
Task 5 |  |  | 0.42857 |  | 0.42857 |  | Task 5 |  |  | 0.3 |  |  | 0.3
Task 6 |  | 0.2 |  |  | 0.2 |  | Task 6 |  |  | 0.5 |  |  | 0.5
Task 7 |  |  | 0.3 |  | 0.3 |  | Task 7 |  | 0.5 |  |  |  | 0.5
Task 8 | 0 |  |  |  | 0 |  | Grand Total | 0 | 0.7 | 0.8 | 0.625 | 0.88889 | 3.0139
Grand Total | 0 | 0.2 | 2.7036 | 0.44444 | 3.348
Project | Gemini
[8 empty] | Project | Orion
Sum of Progress | Days completed
Tasks | 0 | 1 | 2 | 3 | 4 | Grand Total |  | Sum of Progress | Days completed
Task 1 |  |  | 0.4 |  |  | 0.4 |  | Tasks | 0 | 1 | 3 | 4 | 5 | 7 | Grand Total
Task 10 |  |  |  | 0.5 |  | 0.5 |  | Task 1 | [5 empty] | 1 | 1
Task 2 |  |  |  | 0.5 |  | 0.5 |  | Task 10 |  |  | 1 |  |  |  | 1
Task 3 |  |  |  |  | 0.4 | 0.4 |  | Task 2 |  |  |  | 0.44444 |  |  | 0.44444
Task 4 |  |  |  | 0.33333 |  | 0.33333 |  | Task 3 | 0 | [5 empty] | 0
Task 5 |  | 0.25 |  |  |  | 0.25 |  | Task 4 |  |  | 0.42857 |  |  |  | 0.42857
Task 6 | 0 |  |  |  |  | 0 |  | Task 5 |  | 0.25 |  |  |  |  | 0.25
Task 7 |  |  |  | 0.42857 |  | 0.42857 |  | Task 6 |  |  | 0.5 |  |  |  | 0.5
Task 8 |  |  | 0.4 |  |  | 0.4 |  | Task 7 |  |  |  |  | 0.83333 |  | 0.83333
Task 9 |  | 0.11111 |  |  |  | 0.11111 |  | Task 8 |  | 0.25 |  |  |  |  | 0.25
Grand Total | 0 | 0.36111 | 0.8 | 1.7619 | 0.4 | 3.323 |  | Task 9 |  |  | 0.42857 |  |  |  | 0.42857
[8 empty] | Grand Total | 0 | 0.5 | 2.3571 | 0.44444 | 0.83333 | 1 | 5.1349
Project | Vega
Sum of Progress | Days completed
Tasks | 2 | 3 | 4 | 5 | Grand Total
Task 1 |  |  |  | 0.5 | 0.5
Task 2 |  |  | 0.8 |  | 0.8
Task 3 |  | 0.42857 |  |  | 0.42857
Task 4 | 0.28571 |  |  |  | 0.28571
Task 5 | 0.66667 |  |  |  | 0.66667
Grand Total | 0.95238 | 0.42857 | 0.8 | 0.5 | 2.681

## progress -1
Project | (All) | Progress based on tasks and manager for each project
Row Labels | Average of Progress
Task 1 | 0.63278
Hirsch | 0.69722
McFay | 0.375
Task 2 | 0.47778
Samora | 0.48611
Wood | 0.44444
Task 3 | 0.28571
Ladd | 0.6
McFay | 0.20714
Task 4 | 0.53452
Hirsch | 1
Wood | 0.41815
Task 5 | 0.37905
Ladd | 0.36667
Samora | 0.42857
Task 6 | 0.3
Hirsch | 0.33333
McFay | 0.2
Task 7 | 0.51548
Samora | 0.5873
Wood | 0.3
Task 8 | 0.21667
Ladd | 0
McFay | 0.325
Task 9 | 0.26984
Wood | 0.26984
Task 10 | 0.75
Ladd | 0.75
Grand Total | 0.43752

## workings
OVERALL TASK PROGRESS
Not Started | 4 | Values |  |  |  | Scrollbar
In progress | 33 | Sum of Days completed | 112 | Days completed | 42.11% | 14
Completed | 3 | Sum of Duration | 266 | Days remaining | 57.89%
Remaining | 37
Total Tasks | 40
Values
|  | Sum of Days completed | 112
|  | Sum of Duration | 266

## dashboard
DASHBOARD |  | 17-Feb-20 to 2-Mar-20
Project | Task | Manager | Start Date | End Date | Duration | Days completed | Progress | 4387800% | 4387900% | 4388000% | 4388100% | 4388200% | 4388300% | 4388400% | 4388500% | 4388600% | 4388700% | 4388800% | 4388900% | 4389000% | 4389100% | 4389200% | 4389300% | 4389400% | 4389500% | 4389600% | 4389700% | 4389800% | 4389900% | 4390000% | 4390100% | 4390200% | 4390300%
Alpha | Task 1 | McFay | 4388900% | 4390000% | 8 | 3 | 37.5%
| Task 2 | Wood | 4389200% | 4390200% | 9 | 4 | 44.44%
| Task 3 | Ladd | 4388100% | 4388700% | 5 | 3 | 60%
| Task 4 | Hirsch | 4388000% | 4388200% | 3 | 3 | 100%
| Task 5 | Samora | 4388200% | 4389200% | 7 | 3 | 42.86%
| Task 6 | McFay | 4388500% | 4389600% | 10 | 2 | 20%
| Task 7 | Wood | 4388500% | 4389600% | 10 | 3 | 30%
| Task 8 | Ladd | 4388500% | 4388700% | 3 | 0 | 0%
Delta | Task 1 | Hirsch | 4389200% | 4390200% | 9 | 8 | 88.89%
| Task 2 | Samora | 4389200% | 4390300% | 10 | 2 | 20%
| Task 3 | McFay | 4387800% | 4388100% | 4 | 0 | 0%
| Task 4 | Wood | 4388000% | 4388900% | 8 | 5 | 62.5%
| Task 5 | Ladd | 4388500% | 4389600% | 10 | 3 | 30%
| Task 6 | Hirsch | 4388600% | 4389300% | 6 | 3 | 50%
| Task 7 | Samora | 4388600% | 4388900% | 4 | 2 | 50%
Gemini | Task 1 | Hirsch | 4387800% | 4388200% | 5 | 2 | 40%
| Task 10 | Ladd | 4388500% | 4389200% | 6 | 3 | 50%
| Task 2 | Samora | 4387800% | 4388500% | 6 | 3 | 50%
| Task 3 | McFay | 4387900% | 4389200% | 10 | 4 | 40%
| Task 4 | Wood | 4388200% | 4389400% | 9 | 3 | 33.33%
| Task 5 | Ladd | 4387800% | 4388100% | 4 | 1 | 25%
| Task 6 | Hirsch | 4388100% | 4388800% | 6 | 0 | 0%
| Task 7 | Samora | 4388100% | 4388900% | 7 | 3 | 42.86%
| Task 8 | McFay | 4388500% | 4388900% | 5 | 2 | 40%
| Task 9 | Wood | 4388500% | 4389500% | 9 | 1 | 11.11%
Orion | Task 1 | Hirsch | 4387900% | 4388700% | 7 | 7 | 100%
| Task 10 | Ladd | 4387800% | 4388000% | 3 | 3 | 100%
| Task 2 | Samora | 4387800% | 4388800% | 9 | 4 | 44.44%
| Task 3 | McFay | 4387900% | 4388800% | 8 | 0 | 0%
| Task 4 | Wood | 4388100% | 4388900% | 7 | 3 | 42.86%
| Task 5 | Ladd | 4388200% | 4388700% | 4 | 1 | 25%
| Task 6 | Hirsch | 4388200% | 4388900% | 6 | 3 | 50%
| Task 7 | Samora | 4388500% | 4389200% | 6 | 5 | 83.33%
| Task 8 | McFay | 4388600% | 4388900% | 4 | 1 | 25%
| Task 9 | Wood | 4388800% | 4389600% | 7 | 3 | 42.86%
Vega | Task 1 | Hirsch | 4387800% | 4388900% | 10 | 5 | 50%
| Task 2 | Samora | 4388200% | 4388800% | 5 | 4 | 80%
| Task 3 | McFay | 4388500% | 4389300% | 7 | 3 | 42.86%
| Task 4 | Wood | 4388700% | 4389500% | 7 | 2 | 28.57%
| Task 5 | Ladd | 4388900% | 4389300% | 3 | 2 | 66.67%
Grand Total
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.